## Sheet1
TASKS | DATE | TIME (hrs) | NOTES
Research Mouse Input | 2018-05-10 | 0.5 | I could not find out how to move the catcher with the mouse.
Research Arrays | 2018-05-16 | 1 | Array for Raindrops
Move Catcher | May 10-14 | 2.1 | I decided to move the catcher with the arrow keys instead of the mouse.
Move Raindrop | May 18-19 | 3 | Moved raindrops but goes way too fast and can't see it.
Array of Raindrops | May 16-18 | 1.1 | I think I figured out how to but I got rid of when working on speed of raindrops.
Speed of Raindrops | May 21-23 | 3 | I researched and tried a lot of different methods but I could not get it to work.
Organize Data | May 21-23 | 0.5 | Made this table and organized source code for GitHub.
Total | May 10-23 | 11.2 | Unfortunately I couldn't finish the game and figure out how to put all of the pieces together.
Raindrop Catcher game plan:
Goal: make game that has an array of raindrops to move down on the screen so that the user can move the catcher with the mouse to catch the raindrops before they hit the bottom of the screen.
Plan for tasks/ research:
Day 1 and 2: move objects with mouse for catcher
Day 3 and 4: move raindrops down screen
Day 5 and 6: make array of raindrops
Day 7 and 8: collision detection between catcher and raindrops making raindrop disappear
and if time increase score by one.